## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-13 | Documentation | Writing the struct of the protocol | 0:30 | 0:16 | Skill comes with practice
2014-10-13 | Preperation | Configuration of the Hardware Environment | 2:30 | 7:30 | I had some issues finding an improving an existing Makefile, preparing the whole hardware environment(flashing tool, linker, compiler, etc.) and actually testing the whole process by successfully flashing a working program onto the TM4C123GXL
2014-11-13 | Preperation | Using the new Makefile, testing the normal SSI | 2:00 | 2:00 | Flash the spi_slave.c file onto the hardware
2014-11-20 | Implement | Adjust spi_slave.c for master and slave to provide both-sided-communication | 2:00 | 2:00 | Read the documentation + adjusting the files + try n error
SUM |  |  | 7:00 | 11:46

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-11-13 | Preperation | Using the new Makefile, testing the normal SSI | 2:00 | 2:00 | Flash the spi_slave.c file onto the hardware
2014-11-20 | Implement | Adjust spi_slave.c for master and slave to provide both-sided-communication | 2:00 | 2:00 | Read the documentation + adjusting the files + try n error
SUM |  |  | 4:00 | 4:00

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 7:00 | 11:46
| Mair | 4:00 | 4:00
| SUM | 11:00 | 15:46