## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-10-13 | Documentation | Writing the struct of the protocol | 0:30 | 0:16 | Skill comes with practice
2014-10-13 | Preperation | Configuration of the Hardware Environment | 2:30 | 7:30 | I had some issues finding an improving an existing Makefile, preparing the whole hardware environment(flashing tool, linker, compiler, etc.) and actually testing the whole process by successfully flashing a working program onto the TM4C123GXL
SUM |  |  | 3:00 | 7:46

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
SUM |  |  | 0:00 | 0:00

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 3:00 | 7:46
| Mair | 0:00 | 0:00
| SUM | 3:00 | 7:46